SITE SELECTION OPERATING GUIDE

How development teams move from a business need to a defensible site decision

A practical process for large commercial, industrial, infrastructure, and data-center projects

Core idea Site selection is not a map search. It is a sequence of decisions that converts a business requirement into a controlled, buildable, serviceable, approvable, and economically viable site—with evidence retained at every step.

Prepared July 18, 2026

Scope: United States; examples emphasize large-scale industrial and data-center development.

# How to use this guide

Use Sections 1–3 to establish the project brief and the first two weeks of work.

Use Sections 4–11 as the stage-gate operating process.

Use Sections 12–14 as the data sourcing, scoring, and evidence standard.

Use the final checklists to run a project or define product requirements for a site-selection platform.

# Executive summary

A good site-selection process answers five questions in order:

Where should the project compete? — market and jurisdiction screening.

Which actual parcels could support the program? — parcel discovery and hard filters.

What could prevent development? — constraints, infrastructure, legal control, and entitlement path.

What would it cost and how long would it take? — test fit, off-site work, utility schedule, approvals, and risk-adjusted economics.

What evidence is strong enough to commit capital? — source provenance, professional diligence, agency/utility confirmation, and decision approval.

The process should be stage-gated. Early stages use fast, inexpensive screening data. Later stages replace proxies with site-specific evidence. The team should not spend diligence money on a parcel that already fails a hard business requirement, but it should also never treat a national GIS layer, vendor score, or estimated utility distance as final proof.

The key operating distinction Screening answers ‘where should we look?’ Diligence answers ‘can we build this project here on these terms?’ The data standard must become stricter as the project advances.

## Typical decision funnel

| Stage | Typical population | Decision |
| --- | --- | --- |
| Market universe | 50–500 markets / jurisdictions | Where should the search concentrate? |
| Parcel longlist | 100–10,000 parcels | Which parcels survive hard filters? |
| Desktop shortlist | 10–50 sites | Which sites merit owner, utility, and agency outreach? |
| Active candidates | 3–10 sites | Which sites merit test fit, diligence, and site control? |
| Preferred site + backup | 1–2 sites | Where should capital and negotiation attention concentrate? |

## What the final recommendation should contain

A preferred site and at least one credible backup.

A plain-language explanation of why each losing alternative was eliminated.

A site plan or test fit tied to the actual parcel boundary.

Utility, access, water, wastewater, and telecom assumptions with confirmation status.

Entitlement and permit path with dependencies, decision makers, and realistic schedule ranges.

A risk register that separates fatal flaws, mitigable risks, open questions, and accepted assumptions.

A source register so every material claim can be traced to an official record, document page, map layer, or named confirmation.

# 1. Start with the decision—not the map

The first deliverable is a site-selection brief. It is written before searching parcels. Its purpose is to prevent the search from drifting toward whatever happens to be easy to find or visually attractive on a map.

## The site-selection brief

| Brief element | Questions to resolve |
| --- | --- |
| Business objective | What outcome is the facility intended to produce? What launch date or capacity target drives the search? |
| Program | Land area, building area, phasing, parking, loading, yards, setbacks, security, redundancy, and expansion reserve. |
| Infrastructure | Electric load and ramp, voltage, water demand, wastewater discharge, gas, fiber routes, road class, rail or airport needs. |
| Geography | Required customer radius, labor shed, latency, grid region, state restrictions, tax posture, climate, and portfolio strategy. |
| Economics | Land basis, total development budget, off-site allowance, operating-cost ceiling, incentive assumptions, and required return. |
| Schedule | Need-by date, entitlement duration tolerance, utility lead time, acquisition deadline, and phase sequencing. |
| Risk posture | Which conditions are absolute dealbreakers? Which may be mitigated with money, design, schedule, or approvals? |
| Governance | Decision owner, functional reviewers, approval thresholds, documentation standard, and escalation path. |

## Hard filters versus weighted criteria

A hard filter is binary: a candidate that fails is removed unless an authorized person explicitly overrides the rule. A weighted criterion differentiates among otherwise viable candidates. Mixing the two creates bad rankings—for example, a cheap site should not outrank a site that can actually receive the required power by the need date.

| Hard filter examples | Weighted criterion examples |
| --- | --- |
| Minimum usable acreage | Land price and carrying cost |
| Required use allowed or credibly entitlable | Relative entitlement complexity |
| Ability to achieve utility service by need date | Operating utility rate |
| No non-mitigable access or environmental conflict | Labor depth and wage level |
| Owner willing and able to transact | Incentive potential |

# 2. The first ten business days

| When | Work | Output |
| --- | --- | --- |
| Days 1–2 | Interview sponsor and functional leads; document program, need date, economics, and risk posture. | Approved site-selection brief |
| Days 2–3 | Separate hard filters from scored criteria; define evidence required to pass each gate. | Criteria dictionary and gate rules |
| Days 3–4 | Define the market unit, parcel unit, and source hierarchy; identify unavailable or stale data. | Data plan and source register |
| Days 4–6 | Build market and jurisdiction universe; apply true exclusions before scoring. | Market longlist and elimination log |
| Days 6–8 | Assemble parcel universe in priority markets; normalize APNs, ownership, and jurisdictions. | Parcel longlist |
| Days 8–10 | Run desktop fatal-flaw screen; manually verify the highest-ranked candidates. | Initial shortlist and open-question list |

## What not to do first

Do not begin by browsing broker listings; listings are one supply channel, not the search universe.

Do not create a 100-point score before defining fatal flaws and evidence standards.

Do not assume that a parcel boundary, owner name, zoning code, or utility line shown by one vendor is current.

Do not ask utilities for generic capacity. Ask whether a stated load, ramp, redundancy, voltage, and need date can be served at the specific site and what study process is required.

Do not present a ranked list without an elimination log and a statement of unresolved assumptions.

# 3. The end-to-end stage-gate process

| Gate | Purpose | Minimum evidence to advance |
| --- | --- | --- |
| 0 — Search authorized | Approve business need and search rules. | Signed brief, criteria dictionary, budget, decision owner. |
| 1 — Markets qualified | Select markets and jurisdictions worth parcel discovery. | Comparable official data, policy review, known exclusions, documented score. |
| 2 — Parcels qualified | Remove parcels that fail obvious physical, legal, or program rules. | Parcel geometry, ownership, zoning, access, environmental overlays, acreage calculation. |
| 3 — Shortlist approved | Choose candidates for outreach and concept work. | Manual source verification, preliminary utility and entitlement view, owner/contact status. |
| 4 — Active diligence | Authorize site visits, test fits, consultants, and site-control negotiation. | Credible path to control, initial utility/agency feedback, no unresolved obvious fatal flaw. |
| 5 — Preferred site | Select preferred and backup candidates. | Test fit, development budget, schedule, risk register, utility path, entitlement path. |
| 6 — Commit capital | Approve acquisition/lease and full development work. | Site-specific diligence, negotiated terms, professional reports, approved exceptions. |
| 7 — Handoff | Move from selection to acquisition, design, entitlement, and execution. | Controlled data room, decision record, conditions, owners, dates, and monitoring plan. |

# 4. Market and jurisdiction screening

Market screening reduces the search space before parcel work begins. The correct geographic unit depends on the business: labor shed for manufacturing, latency and network geography for digital infrastructure, customer service radius for logistics, grid region for power-intensive facilities, or a combination.

## Typical market criteria

Demand and customer access: population, business base, freight flows, delivery radius, latency, or portfolio coverage.

Labor: relevant occupations, employment concentration, wages, growth, commuting shed, competition, and training pipeline.

Infrastructure: highway and rail access, airports, ports, utility territories, generation/transmission context, fiber, water, and wastewater.

Policy and approvals: allowed uses, moratoria, local plans, prior decisions, permit sequence, political sensitivity, and agency capacity.

Economics: land, taxes, rates, construction costs, incentives, insurance, and expected off-site obligations.

Hazard and resilience: flood, wildfire, wind, heat, drought/water stress, seismic exposure, and business-continuity requirements.

Market scores should use comparable vintages and geographic levels. County employment data should not be compared directly with metropolitan data without normalization. A jurisdiction score should retain the ordinance, plan, meeting record, or decision history behind each indicator rather than reduce the jurisdiction to an unexplained number.

# 5. Parcel discovery and ownership resolution

Parcel discovery combines the official cadastral or tax parcel fabric with supply sources. Teams use county assessor/GIS downloads, state parcel programs where available, broker and landowner lists, economic-development inventories, proprietary parcel platforms, and direct outreach. No single source is complete.

## Minimum parcel record

Canonical parcel ID/APN, county, municipality, and coordinate reference system.

Current and prior geometry with source and retrieval date.

Recorded owner, tax-mailing owner, related entities, and contact confidence.

Gross acreage, estimated usable acreage, contiguous ownership group, and assemblage dependencies.

Zoning/base district, overlays, future land-use designation, and comprehensive-plan context.

Road frontage, legal/physical access evidence, adjacent rights-of-way, and rail/utility proximity.

Listing or owner-interest status, asking terms, transaction history, and site-control constraints.

Identity problem Addresses are not stable parcel identifiers. APNs can be reformatted, retired, split, or merged. A robust record keeps the source jurisdiction, normalized APN, source APN, geometry version, and parent/child relationships.

# 6. Desktop fatal-flaw screening

Desktop screening is a fast triage, not final diligence. Each rule should return one of four states: pass, fail, review, or unknown. Unknown is not pass.

| Constraint family | Desktop questions | Escalation / confirmation |
| --- | --- | --- |
| Program fit | Is gross and estimated usable acreage sufficient? Can required dimensions and buffers fit? | Concept test fit; boundary/topographic survey. |
| Land use | Is the use allowed, conditional, or prohibited? Are overlays or plan policies relevant? | Planner interpretation; land-use counsel; pre-application meeting. |
| Flood / drainage | Does effective flood mapping overlap? Are waterways, drainageways, or local flood layers present? | Civil study, survey, hydrology; local floodplain administrator. |
| Wetlands / habitat | Do mapped wetlands, waters, habitat, or species records indicate likely impact? | Field delineation, habitat survey, agency coordination. |
| Soils / terrain | Do slope, soil, karst, expansive soil, or bearing indicators create risk? | Geotechnical borings and engineered grading concept. |
| Access | Is there frontage and a plausible legal/physical access route? Are turn or interchange constraints obvious? | Title/survey review; traffic engineer; DOT or road authority. |
| Utilities | Are service territories and nearby facilities known? Is the requirement plausible? | Named utility intake, study, engineering response, and commercial terms. |
| Environmental history | Are regulated facilities, historic uses, tanks, waste, or enforcement records nearby? | Phase I ESA and follow-up investigation. |

# 7. Infrastructure feasibility

Infrastructure often determines the real shortlist. Distance to a line or facility is only a proxy. Capacity, protection requirements, right-of-way, network topology, upgrades, cost allocation, construction sequencing, and study queues determine serviceability.

## A proper utility request

Exact site and parcel boundary—not only a city or ZIP code.

Initial load, full build-out load, monthly/annual profile, and ramp schedule.

Required in-service date and interim-service needs.

Voltage, reliability, redundancy, power-quality, generation, storage, and backup assumptions.

Water demand by day and peak; wastewater quantity and quality; fire-flow requirements.

Requested response: service point, study process, schedule range, upgrade scope, commercial terms, dependencies, and confidence level.

For power-intensive projects, EIA, FERC, ISO/RTO, utility maps, and public planning materials help establish regional context, but they do not prove that a specific large load can connect by a specific date. That conclusion must come from the serving utility and applicable grid-study process. [S10–S12]

# 8. Jurisdiction and entitlement feasibility

A zoning label is only the first question. The team needs the full approval path and the local decision context.

Confirm the governing jurisdiction, extraterritorial area, annexation status, special districts, and overlapping authorities.

Read the use table, definitions, dimensional standards, overlays, performance standards, and adopted plans.

Map every required legislative, quasi-judicial, administrative, utility, environmental, building, and operational approval.

Review recent staff reports, conditions, hearing minutes, votes, appeals, and comparable project outcomes.

Identify pre-application requirements, submittal windows, completeness rules, public notice, hearing cadence, and appeal periods.

Track active moratoria, pending ordinances, comprehensive-plan updates, elections, leadership changes, and organized opposition.

Source hierarchy for land-use conclusions Adopted ordinance and official map → formal written interpretation or agency record → adopted plan and staff report → meeting record → practitioner interpretation → vendor classification. Record conflicts; do not silently choose the most favorable source.

# 9. Site visit, test fit, and preliminary engineering

The site visit tests assumptions that maps do not capture: grade transitions, drainage, access geometry, adjacent uses, overhead lines, encroachments, neighborhood context, visible environmental conditions, construction logistics, and the credibility of nearby infrastructure.

## The first test fit should show

Actual parcel boundary and any assemblage parcels.

Building, equipment yards, parking, loading, security, stormwater, setbacks, buffers, and expansion area.

Known flood, wetland, easement, utility, topographic, access, and zoning constraints.

Assumptions that are not yet surveyed or confirmed.

Alternatives that demonstrate which constraint controls usable capacity.

A reconciliation of gross acreage, constrained acreage, and usable development area.

# 10. Site control and professional diligence

Before expensive diligence, the team seeks credible site control—purchase agreement, option, lease, exclusivity, or other structure—with enough time, access rights, extension mechanics, assignment rights, and termination conditions to complete approvals and infrastructure studies.

## Common diligence workstreams

| Workstream | Primary deliverable | What it replaces |
| --- | --- | --- |
| Title and survey | Title commitment/report, exception documents, ALTA/NSPS or jurisdiction-appropriate survey | Assessor geometry, approximate access, assumed easements |
| Environmental | Phase I ESA; Phase II or specialist work if triggered | Database-only environmental screen |
| Wetlands / waters / habitat | Field delineation, jurisdictional strategy, species/habitat studies | National wetlands and habitat overlays |
| Geotechnical | Borings, lab results, foundation and earthwork recommendations | Soil survey and regional geology proxies |
| Civil / drainage | Topo, grading, drainage, utility, and access concepts | Desktop slope and distance analysis |
| Traffic / access | Access concept, traffic study, agency feedback | Road proximity and generic classification |
| Utilities | Studies, service letters/agreements, upgrade scope, schedule, and cost | Line proximity and service-territory assumptions |
| Land use | Written path, application strategy, schedule, and conditions risk | Vendor zoning label |

# 11. Recommendation, approval, and handoff

The recommendation should be a decision package, not a score screenshot. A strong package explains what is known, what is inferred, what remains open, who owns each open item, and what would change the recommendation.

## Required decision exhibits

Executive comparison of preferred site and backups.

Criteria score with separate hard-filter status and evidence confidence.

Parcel map and test fit.

Land, entitlement, utility, design, and construction schedule with dependencies.

Risk-adjusted development budget and scenario ranges.

Conditions and exceptions requiring executive acceptance.

Source register and diligence index.

Handoff matrix: task, owner, due date, approval gate, and dependent documents.

# 12. Where site-selection teams get data

Teams use a layered sourcing model. National data creates a consistent screen. Local official records establish parcel and legal context. Commercial sources improve speed, coverage, and contactability. Site-specific professional work and written agency/utility confirmation support capital commitment.

## National and federal screening sources

| Need | Primary source | Good for | Important limitation |
| --- | --- | --- | --- |
| Flood | FEMA Map Service Center / NFHL [S1] | Effective flood hazard mapping and map products | Coverage and effective dates vary; local and project-specific studies may control. |
| Wetlands | USFWS National Wetlands Inventory [S2] | Desktop wetland/deepwater screening and metadata | Not a field delineation or jurisdictional determination. |
| Soils | USDA NRCS Web Soil Survey / SSURGO [S3] | Soil properties and map units for early screening | Not a substitute for borings or geotechnical design. |
| Elevation | USGS 3DEP / The National Map [S4] | Terrain, slope, contours, and regional grading screen | Resolution and acquisition vintage vary; survey controls design. |
| Regulated facilities | EPA ECHO [S5] | Nearby regulated facilities, permits, compliance, and enforcement context | Not a complete environmental condition opinion; Phase I process remains necessary. |
| Boundaries / roads | Census TIGER/Line [S6] | Consistent legal/statistical boundaries and many transportation features | Not parcel geometry; not a survey or legal boundary determination. |
| Demographics | Census data and API [S7] | Population, households, commuting and business context | Geographic scale and vintage must match the question. |
| Labor / wages | BLS QCEW [S8] | County/MSA employment and wage data by industry | Released with lag and revisions; occupation-level questions need additional BLS/state sources. |
| Broadband | FCC National Broadband Map [S9] | Reported service availability screening | Provider-reported availability is not a fiber route, diversity, price, or service commitment. |
| Energy context | EIA Open Data [S10] | State/sector rates, generation, demand, and system context | Not proof of site-specific capacity or delivery schedule. |
| Grid / market structure | FERC and relevant ISO/RTO [S11–S12] | Market footprint, transmission planning context, tariffs and proceedings | Large-load serviceability remains a site-specific utility/grid determination. |

## Local official sources

| Source | Typical owner | What teams retrieve |
| --- | --- | --- |
| Assessor / tax parcel | County assessor, property appraiser, or GIS office | APN, tax owner, mailing address, assessed facts, parcel geometry. |
| Recorder / clerk | County recorder, register of deeds, clerk | Deeds, liens where available, plats, easements, recorded restrictions, transaction evidence. |
| Planning / zoning | City or county planning department | Official zoning map, code, use tables, overlays, comprehensive plan, applications, interpretations. |
| Meeting records | Clerk, planning commission, council, board of adjustment | Agendas, staff reports, conditions, minutes, video, votes, appeals, public comments. |
| Permit portal | Building, development services, public works | Permit history, application status, inspection history, fee schedules, submittal requirements. |
| Transportation | State DOT, MPO, city/county road authority | Road ownership, functional class, access management, planned projects, traffic counts, freight routes. |
| Environment / water | State environmental agency, water district, floodplain office | Permits, impaired waters, water rights/allocation, local flood data, discharge requirements. |
| Utilities | Electric, gas, water, wastewater, telecom provider | Service territory, intake process, studies, service point, capacity, upgrades, cost, and schedule. |
| Economic development | State/local development authority | Site inventories, incentives, workforce programs, agency coordination, known development history. |

## Commercial and team-provided sources

Commercial platforms may aggregate parcels, listings, ownership, transactions, contacts, zoning, utilities, environmental layers, mobility, costs, and market forecasts. They are useful for speed and normalization, but the team should retain the vendor, vintage, license restrictions, and source lineage—and verify decision-critical fields against authoritative records.

Broker and landowner submissions: supply, asking terms, ownership context, off-market opportunities.

Title and transaction platforms: recorded documents, transaction history, entity relationships.

Parcel/GIS vendors: normalized national parcel fabric and prejoined attributes.

Market and cost vendors: rents, land comps, construction cost, taxes, incentives, forecasts.

Utility and telecom consultants: service-territory intelligence, process experience, network context.

Internal portfolio data: actual development cost, schedule, approvals, operating performance, and failure history.

# 13. The evidence and provenance standard

Every material field or conclusion should carry enough metadata to answer: who published it, what exactly was retrieved, when it was retrieved, when it became effective, what geography it covers, how it was transformed, and whether it has been confirmed.

| Field | Minimum metadata |
| --- | --- |
| Document fact | Source file/URL, publisher, document date, retrieved date, page/section, quoted or normalized value. |
| GIS fact | Layer name, publisher, service/download URL, version/effective date, retrieved date, CRS, scale/resolution, geometry operation. |
| Vendor attribute | Vendor, product, attribute definition, data vintage, original source if provided, confidence, license restrictions. |
| Human confirmation | Person, organization, role, date, site/load/program described, medium, exact statement, follow-up required. |
| Derived score | Input fields and vintages, formula, hard-filter result, weight version, missing-data treatment, override history. |

## Reliability ladder

Level 1 — Site-specific executed or professional evidence: recorded instrument, survey, study, service agreement, permit, approved plan.

Level 2 — Formal written confirmation: utility/agency letter, written interpretation, official meeting or application record.

Level 3 — Adopted official source: ordinance, official map, adopted plan, effective federal/state/local dataset.

Level 4 — Aggregated or commercial source: normalized vendor field, listing, broker package, contact dataset.

Level 5 — Inference or proxy: distance, modelled score, image interpretation, unverified oral statement.

The required level depends on the gate. Level 4–5 may be enough for market screening. A capital-commitment decision generally requires Level 1–2 for the risks that could stop the project.

# 14. Scoring without hiding the decision

Scoring is useful only after hard filters, and only when the score remains explainable. The goal is consistent comparison—not mathematical certainty.

| Rule | Practical implementation |
| --- | --- |
| Separate viability from preference | Show hard-filter status beside the weighted score. |
| Use observable metrics | Define exactly how acreage, schedule, cost, risk, or labor is calculated. |
| Normalize carefully | Use comparable geography, units, vintages, directionality, and outlier treatment. |
| Do not reward missing data | Unknown should reduce confidence or block advancement; it should not silently receive an average score. |
| Show sensitivity | Re-rank with alternative weights and cost/schedule assumptions. |
| Retain overrides | Record who overrode what rule, why, when, and what evidence supported the decision. |
| Track confidence | A high score based on weak evidence should not outrank a slightly lower score based on confirmed evidence without explicit review. |

## Example scoring structure

| Dimension | Example weight | Example measures |
| --- | --- | --- |
| Infrastructure and service date | 30% | Power/water/fiber path, schedule, redundancy, upgrade exposure. |
| Physical feasibility | 20% | Usable area, terrain, drainage, access, constraints, expansion. |
| Land use and approvals | 15% | Allowed use, approval path, precedent, conditions, political risk. |
| Economics | 15% | Land, off-site work, rates, tax, incentives, operating cost. |
| Market and labor | 10% | Demand/customer access, labor depth, wage, competition. |
| Resilience and external risk | 10% | Hazards, water stress, insurance, opposition, change risk. |

Illustrative only. The site-selection brief should determine weights; the tool should never make business priorities appear objective by default.

# 15. Data-center-specific additions

For data centers, power and schedule usually dominate the funnel, but land-use, water, fiber, noise, generators, air permits, tax posture, and public acceptance can become controlling constraints.

Define MW by phase, ramp, coincidence, power factor, voltage, redundancy, and in-service dates.

Map utility, balancing authority, RTO/ISO, tariff, large-load rules, transmission/substation context, and study path—but treat these as context until the serving utility confirms the site.

Evaluate fiber providers, physically diverse routes, meet-me/interconnection options, latency, and rights-of-way rather than simple broadband availability.

Quantify water by design and operating mode; include peak, drought restrictions, quality, discharge, and alternative cooling scenarios.

Screen generator fuel, emissions permitting, testing hours, noise, setbacks, hazardous materials, fire code, and community sensitivity.

Track moratoria, large-load tariffs, tax/incentive changes, comprehensive-plan amendments, utility queue rules, and public opposition continuously.

# 16. Common failure modes

| Failure | Why it happens | Control |
| --- | --- | --- |
| The score chooses the site | Weights hide business judgment and evidence quality. | Hard filters, confidence rating, sensitivity, and approval gate. |
| Map overlap treated as legal fact | Screening layer is easier to use than the controlling record. | Source hierarchy and professional confirmation. |
| Power line equals power capacity | Distance is visible; system capacity and schedule are not. | Site-specific utility intake and study. |
| Zoning label equals entitlement path | Use table, overlays, definitions, and process are skipped. | Full code review, staff history, and agency confirmation. |
| Owner record equals site control | Tax owner may be stale or an entity with complex authority. | Recorded documents, entity resolution, authority and negotiation checks. |
| Unknown becomes average | Incomplete data is forced into a ranking. | Explicit unknown state, confidence penalty, or gate block. |
| No backup site | Team overinvests emotionally and commercially in one candidate. | Maintain a credible backup through the preferred-site gate. |
| Source disappears | Web map, meeting packet, or vendor field changes. | Retain retrieval date, copy/reference, metadata, and version. |

# 17. Team, cadence, and decision rights

| Role | Primary responsibility |
| --- | --- |
| Executive sponsor / investment owner | Business case, priorities, risk acceptance, capital gates. |
| Site-selection lead | Process, criteria, search universe, comparison, recommendation, decision log. |
| Real estate / acquisitions | Owner contact, site control, valuation, negotiations, transaction diligence. |
| GIS / data | Source register, parcel identity, spatial analysis, reproducibility, evidence lineage. |
| Utilities / infrastructure | Load/service request, studies, upgrade scope, schedule, cost, commercial path. |
| Design / engineering | Program, test fit, access, grading, drainage, constructability, estimate. |
| Land use / legal | Title, code, approvals, restrictions, conditions, hearings, transaction documents. |
| Environmental | Environmental, wetlands, habitat, permitting and remediation workstreams. |
| Government / community | Agency process, incentives, public engagement, opposition and change monitoring. |

A weekly site-selection meeting should review only changes, gate decisions, material risks, and owner actions. The detailed evidence stays in the project record; the meeting should not become a tour of every map layer.

# 18. Operator checklists

## Before parcel search

☐ Business objective and need date approved

☐ Program and phasing defined

☐ Hard filters separated from weights

☐ Evidence standard defined by gate

☐ Geographic unit and search boundary defined

☐ Decision owner and reviewers named

## Before shortlist approval

☐ Parcel ID, geometry, ownership, and jurisdiction manually checked

☐ Zoning/use and plan context reviewed from official sources

☐ Environmental and physical screen complete

☐ Access and infrastructure paths plausible

☐ Owner/contact status known

☐ Open assumptions and confidence visible

## Before preferred-site approval

☐ Test fit tied to actual boundary

☐ Utility intake and schedule path documented

☐ Entitlement matrix and decision history reviewed

☐ Development budget and schedule include off-site work

☐ Site-control terms support diligence and approvals

☐ Backup site remains viable

☐ Risk register and evidence register current

## Before capital commitment

☐ Survey/title and exception review complete

☐ Environmental/geotech/civil work complete to required gate

☐ Serviceability evidence meets project standard

☐ Approval path and conditions risk accepted

☐ Commercial terms and termination rights approved

☐ Material unknowns assigned and accepted

☐ Decision record signed and handoff owners established

# Sources

[S1] FEMA Flood Maps and National Flood Hazard Layer. Accessed July 18, 2026.

[S2] U.S. Fish & Wildlife Service National Wetlands Inventory — Wetlands Data. Accessed July 18, 2026.

[S3] USDA NRCS Web Soil Survey / SSURGO. Accessed July 18, 2026.

[S4] U.S. Geological Survey 3D Elevation Program. Accessed July 18, 2026.

[S5] U.S. EPA Enforcement and Compliance History Online — About the Data. Accessed July 18, 2026.

[S6] U.S. Census Bureau TIGER/Line Shapefiles. Accessed July 18, 2026.

[S7] U.S. Census Bureau Data API User Guide. Accessed July 18, 2026.

[S8] U.S. Bureau of Labor Statistics Quarterly Census of Employment and Wages. Accessed July 18, 2026.

[S9] FCC National Broadband Map. Accessed July 18, 2026.

[S10] U.S. Energy Information Administration Open Data. Accessed July 18, 2026.

[S11] Federal Energy Regulatory Commission — RTOs and ISOs. Accessed July 18, 2026.

[S12] Federal Energy Regulatory Commission — Electric Power Markets. Accessed July 18, 2026.

Local sources vary by jurisdiction. For each project, add the specific assessor, recorder, zoning code/map, adopted plan, meeting record, permitting portal, DOT/road authority, environmental agency, utility, and project-file references to the source register.